## Sheet1
Task ID (001-...) | Task Name / Task Description | Owner | Priority (High/Medium/Low) | Status (Not Started/In Progress/Completed) | Start Date (DD/MMM) | Due Date (DD/MMM) | % Complete | Depends On (Task ID) | Blockers | Next Steps | Notes
1 | Develop a function to classify text content | Adhirath, Prasanna, Yogeswara | High | Completed | 2025-01-08 | 2025-06-08 | 100% |  |  | Convert the function into API
2 | Convert the classification function into an API (Task ID 1) | Adhirath, Prasanna, Yogeswara | High | Completed | 2025-06-08 | 2025-07-08 | 100% | 1 |  | Deploy the developed API in Cloud Run
3 | Deploy the developed API in Cloud Run (Task ID 2) | Adhirath, Prasanna, Yogeswara | High | Completed | 2025-07-08 | 2025-08-08 | 100% | 2
4 | Write a function to generate quizzes using gemini-2.5-pro, save the quizzes in relevant format in the existing database | Aanandhini | High | Completed | 2025-08-08 | 2025-11-08 | 100%
5 | Convert the quiz generation function into an API | Aanandhini | High | Completed | 2025-12-08 | 8/13/2025 | 100% | 4
6 | Deploy and test the API (Task ID 5) | Aanandhini | High | Completed | 8/13/2025 | 8/13/2025 | 100% | 5
7 | Optimize the Dockerfile to reduce the image size and decrease time to deploy without missing necessary modules | Adhirath | High | Completed | 8/14/2025 | 8/14/2025 | 100% |  |  |  | Requested access to work
8 | Create a working trigger to activate whenever a document is created in tcs-salsa/(default)/user_posts | Adhirath | High | On hold (alternatives being explored) | 8/13/2025 | - | 50% |  | Require relevant permissions from Manoj to execute the task
9 | User activity based personalization (share, like, comment, dislike) | Adhirath, Prasanna, Yogeswara | High | On hold (Basic approach implementation prioritized) | 2025-11-08 | - | - | 1
10 | Creation and finalization of frontend design | C4L Team | High | Terminated (Native changes required) | - | - | -
11 | Implement a reward system for quiz to encourage regular user visit. | Aanandhini | Medium | In Progress | 8/19/2025 | 8/23/2025
12 | Create a logic for push notification to user whenever a new quiz goes live | Aanandhini | Medium | In Progress | 8/20/2025 | 8/25/2025 |  |  | Need guidance from Sitanshu on sending push notifications
13 | Developing Web View (Personalied Blogs, replacing My Timeline) | Srinath | High | Not Started

## Plan
Task ID | Task | Owner | Status | % Complete | Start | Due

## Tracking
date | user | task_id | when | morning_focus | evening_status | blocker_notes | last_updated_ist